# AI Website Lead Qualifier — V1 Milestone & Delivery Plan

Total Project Cost: $4,000 USD
Estimated Timeline: 8–12 weeks

## Milestone 1 — SaaS Foundation & AI Knowledge System

$500 | Weeks 1–3

- SaaS architecture and database

- Multi-tenant account structure

- User authentication

- Support for up to 3 websites/account

- Website URL crawling

- PDF/document upload

- Manual FAQ/text knowledge

- RAG/vector knowledge retrieval

- Embeddable JavaScript chat widget

- Responsive chat interface

- AI conversation engine

- Basic chatbot personality/welcome configuration

Deliverable: Working SaaS foundation with AI-powered website chat and knowledge base.

## Milestone 2 — Qualification, Lead Capture & AI Scoring

$1,250 | Weeks 4–6

- Qualification workflow

- Predefined/AI-generated questions

- Lead information capture

- Consent/privacy handling

- Configurable lead scoring

- Budget: 0–25

- Timeline: 0–20

- Service/Product Interest: 0–20

- Company/Business Fit: 0–15

- Buying Intent: 0–20

- Hot/Warm/Cold classification

- AI lead summary

- Recommended next sales action

- Conversation history

Deliverable: Complete visitor-to-qualified-lead workflow.

## Milestone 3 — Lead Dashboard & Integrations

$1,250 | Weeks 7–9

- Lead management dashboard

- Search and filtering

- Hot/Warm/Cold views

- Lead status/source

- Lead score

- AI summary

- Internal notes

- Follow-up date

- CSV export

- HubSpot integration

- Generic REST Webhook

- Gmail/Google Workspace SMTP

- Outlook/Microsoft 365 SMTP

- Custom SMTP

- New lead and hot-lead email notifications

Deliverable: Complete sales management and integration layer.

## Milestone 4 — Security, Testing & Production Deployment

$1,000 | Weeks 10–12

- Security implementation/review

- Role-based access

- GDPR consent records

- Data export/account deletion

- API credential protection

- Functional testing

- AI/RAG testing

- Multi-website testing

- HubSpot/Webhook testing

- SMTP testing

- Responsive testing

- Performance optimization

- Production deployment

- Bug fixing and stabilization

- Technical handover/documentation

Deliverable: Tested and production-ready V1.

# Payment & Delivery Summary

| Milestone | Cost | Estimated Timeline | Through |
| --- | --- | --- | --- |
| 1. SaaS Foundation & AI Knowledge | $5,00 | Weeks 1–3 | Qfreelancer |
| 2. Qualification & Lead Scoring | $1,250 | Weeks 4–6 | Direct |
| 3. Dashboard & Integrations | $1,250 | Weeks 7–9 | Direct |
| 4. Security, Testing & Deployment | $1,000 | Weeks 10–12 | Direct |
| Total | $4,000 | 8–12 weeks |  |

## V1 Core Workflow

Visitor → AI Chat → Knowledge Base → Qualification → Lead Capture → AI Scoring → Hot/Warm/Cold → AI Summary → Dashboard → Email → HubSpot/Webhook

## Future Phase

The following are outside the V1 fixed scope and can be added later:

- Salesforce, Zoho and Pipedrive

- Stripe/PayPal SaaS billing

- WordPress/Shopify integrations

- Unlimited websites

- AI Sales Agent

- AI objection handling

- Predictive scoring

- Automated lead nurturing

- Appointment/calendar automation

- Visitor company identification

- Returning visitor recognition

- Revenue attribution

- Advanced analytics

- Advanced team-management features

The $4,000 fixed price applies specifically to the V1 scope above. Additional features, integrations or significant changes to the agreed requirements will be estimated separately.

The 8–12 week timeline assumes timely access to API credentials, HubSpot test access, SMTP configuration, website/PDF content and required feedback/approvals.

A short post-launch stabilization period is included for fixing bugs related to the agreed V1 functionality. New features or scope changes will be handled separately.